## About
ABOUT THIS GANTT CHART
Visualise and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Dark
Birdston Kennels Webpage - With Booking System
[6 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Mid risk |  |  |  |  | High risk |  |  |  |  | Unassigned
| Project lead | James Park
| Project Start Date: | 2023-03-17 |  |  |  |  | March | [20 empty] | April | [27 empty] | May | [27 empty] | June
 | time axis 2023-03-17 to 2023-06-13
| Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-03-17 to 2023-06-13
1 Planning Phase
| 1.1 Start Planning Stage | Low Risk |  |  | 2023-03-17 | 1
| 1.2.1 Create Customer Questionair | On Track | James Park | 100% | 2023-03-18 | 1
| 1.2.2 Submit Quastionair | Milestone |  | 100% | 2023-03-19 | 1 | bar: 2023-03-19
| 1.3 Work out non-functional and functional requirements from the results of the questionair | Low Risk | James Park | 100% | 2023-03-19 | 3
| 1.4.1 Create the planning report | Low Risk | James Park | 100% | 2023-03-22 | 7
| 1.4.2 Submit Planning Report | Milestone |  | 100% | 2023-03-29 | 1 | bar: 2023-03-29
| 1.6.1 Create Class Diagrams | Low Risk | James Park | 100% | 2023-03-29 | 3
| 1.6.2 Create Use Case Diagrams | Low Risk | James Park | 100% | 2023-04-01 | 3
| 1.6.3 Create activity Diagrams | Low Risk | James Park | 100% | 2023-04-04 | 3 | bar: 2023-05-08
| 1.6.4 Create sequence Diagrams | Low Risk | James Park | 100% | 2023-04-07 | 3
| 1.7 Create Screen Layouts | Low Risk | James Park | 100% | 2023-04-10 | 7
| 1. 8 Hand in UML Diagrams and Screen Layouts | Milestone |  | 0% | 2023-04-17 | 1 | bar: 2023-04-17
2 Development Phase
| 2.1 Start Development Stage | Goal |  |  | 2023-04-17 | 1 | 2023-04-17: 2
| 2.2 Create GitHub Repository | Med Risk | James Park | 100% | 2023-04-17 | 1
| 2.3 Create Poco Classes, database context and initializer, user roles, and view models | Low Risk | James Park | 0% | 2023-04-17 | 1
| 2.4.1 Create User Roles | Low Risk | James Park | 0% | 2023-04-18 | 1
| 2.4.2 Seed Database | Low Risk | James Park | 0% | 2023-04-19 | 1
| 2.5 Create Login and Register Views | Low Risk | James Park | 100% | 2023-04-20 | 2
| 2.6 Research logging in and registering with third party i.e. facebook and google | Med Risk | James Park | 50% | 2023-04-22 | 1
| 2.6.2 Implimnent logging in and registering with third party i.e. facebook and google | Low Risk | James Park | 0% | 2023-04-22 | 2
| 2.7 Have logins and registration working | Milestone | James Park | 0% | 2023-04-24 | 1 | bar: 2023-04-24
| 2.8 Create Home Page and have redirects to social media pages | Low Risk | James Park | 50% | 2023-04-24 | 1
| 2.9 Create Information Page | Low Risk | James Park | 100% | 2023-04-25 | 1
| 2.10 Create contact page, with function to allow users to send contact messaged | Low Risk | James Park | 50% | 2023-04-26 | 2
| 2.11 Create user account/profile pages including the functionality to edit account information/add pet(s) information | Low Risk | James Park | 50% | 2023-04-28 | 2
| 2.12 Create Bookings pages with calander showing allowed and unallowed days and the functionality for uses to create bookings | Low Risk | James Park | 50% | 2023-04-30 | 1
| 2.13.1 Research implimentation of payment gateways | Med Risk | James Park | 0% | 2023-05-01 | 2
| 2.13.2 Impliment payment gate way MAKE SURE IT IS A SANDBOX | Low Risk | James Park | 0% | 2023-05-03 | 2
| 2.14 Allow users to save cards to their account [hash card details] | Low Risk | James Park | 0% | 2023-05-05 | 1
| 2.15 Start work on Employee views | Milestone | James Park | 0% | 2023-05-06 | 1 | bar: 2023-05-06
| 2.17 Create functionality for employees to edit the information for amenities via amenities manager views | Low Risk | James Park | 0% | 2023-05-07 | 2
| 2.18 create booking manager page and functionality | Low Risk | James Park | 50% | 2023-05-09 | 2
| 2.19.1 Research sending reminder emails to users | Med Risk | James Park | 0% | 2023-05-11 | 2
| 2.19.2 Impliment the functionality of sending users reminder emails shortly before their booking | Low Risk | James Park | 0% | 2023-05-13 | 1
| 2.20 Create Admin functionality for managing Employee roster and rotas | Low Risk | James Park | 0% | 2023-05-14 | 2
| 2.21 Create functionality for exporting buisness related documentation | Med Risk | James Park | 0% | 2023-05-16 | 1
| 2.22 Fully impliment Design features | Low Risk | James Park | 0% | 2023-05-17 | 3
3 Testing
| 3.1 Start work on Testing | Milestone | James Park | 0% | 2023-05-20 | 1 | bar: 2023-05-20
| 3.2 Create testing strategy document | Low Risk | James Park | 0% | 2023-05-20 | 1
| 3.3 Carry out all test cases and fix any issues | Low Risk | James Park | 0% | 2023-05-21 | 1
| 3.4 Print all screen layouts | Low Risk | James Park | 0% | 2023-05-22 | 1
| 3.5 Print all test logs | Low Risk | James Park | 0% | 2023-05-22 | 5
| 3.6 Create user manual and update Gantt Chart | Low Risk | James Park | 0% | 2023-05-27 | 1
| 3.7 Submit Development stage | Milestone |  | 0% | 2023-05-27 | 1 | bar: 2023-05-27
4 Evaluation Phase
S | 4.1 Start Evaluation Stage | Goal | James Park | 0% | 2023-05-27 | 1 | 2023-05-27: 2
| 4.2 Create the assignment outline documentation | Low Risk | James Park | 0% | 2023-05-28 | 1
| 4.3 Assess strengths and weaknesses | Low Risk | James Park | 0% | 2023-05-29 | 1
| 4.4 Highlight any modification made to the plan over the lifespan of the project | Low Risk | James Park | 0% | 2023-05-30 | 2 | bar: 2023-05-06
| 4.5 Highlight all knowlage and skills gained over the life of the project | Low Risk | James Park | 0% | 2023-06-01 | 2
| 4.6 Highlight any recomendations for improvement of the system created and explain the recommendation | Low Risk | James Park | 0% | 2023-06-03 | 2
| 4.7 Submit Evaluation | Milestone |  | 0% | 2023-06-04 | 1 | bar: 2023-06-04